## {team name} PI Roadmap
EcoStyle PI ROADMAP
| PI 1 |  | PI 2 |  | PI 3 | [7 empty] | PI 4
| S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16
Technical Report 1
Description of Domain Structure | bar: PI 1 S1
Review of Alternative Solutions | bar: PI 1 S1
Vision Statement | bar: PI 1 S1
Open Source Licences | bar: PI 1 S1
Process and Design Documentation
Project Management Plan | bar: PI 1 S2
Quality Assurance Plan | bar: PI 1 S2
Risk Register | bar: PI 1 S2
Project Roadmap | bar: PI 1 S2
Potential Solution Architecture | bar: PI 1 S2
Program Backlog | bar: PI 1 S2
Foundational Setup and Core Features
Project Setup and Configuration | bar: PI 2 S3
User Management and Authentication | bar: PI 2 S3
Product Management System | bar: PI 2 S4
Shopping Cart and Checkout | bar: PI 2 S4
Enhanced User Experience and Admin Tools
UI/UX Design Implementation | bar: PI 3 S5 to PI 3 S7
Product Reviews and Ratings | bar: PI 3 S6 to PI 3 S7
Address Management and Geolocation | bar: PI 3 S7 to PI 3 S8
Order Management and Tracking | bar: PI 3 S8 to PI 3 S9
Admin Dashboard Development | bar: PI 3 S9 to PI 3 S10
Advanced Stock and Inventory Management | bar: PI 3 S10 to PI 3 S11
Financial Management and Refunds | bar: PI 3 S10 to PI 3 S11
System Monitoring and Analytics | bar: PI 3 S11 to PI 3 S12
Delivery Integration and Final Launch
Delivery Service Integration | bar: PI 4 S13
Final System Optimization | bar: PI 4 S13 to PI 4 S14
User Feedback and Iterations | bar: PI 4 S14 to PI 4 S15
Final Testing and Deployment Preparation | bar: PI 4 S14 to PI 4 S16